## Sheet1
M1 Junctions 13 - 16 (15 November 2021–21 November 2021)
Date | Duration | Details | Project | Junction affected | Allow an extra | Diversion Route
Northbound
Monday 15 November | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J15a-J16 | 2 Minutes | N/A
Monday 15 November for 4 nights | 10pm - 6am | Entry slip closure | M1 J13-J16 | J15a | 15 Minutes | J15a south entry to J15 and return
Tuesday 16 November | 10pm - 6am | Lanes 3 and 2 closure | M1 J13-J16 | J15-J15a | 2 Minutes | N/A
Wednesday 17 November for 2 nights | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J14-J15 | 2 Minutes | N/A
Wednesday 17 November for 2 nights | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J15a-J16 | 2 Minutes | N/A
Wednesday 17 November | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J13-J14 | 2 Minutes | N/A
Thursday 18 November | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J14-J15 | 2 Minutes | N/A
Thursday 18 November | 10pm - 6am | Lanes 3 and 2 closure | M1 J13-J16 | J15-J15a | 2 Minutes | N/A
Friday 19 November | 10pm - 6am | Lanes 3 and 2 closure | M1 J13-J16 | J13-J14 | 2 Minutes | N/A
Friday 19 November | 10pm - 6am | Lanes 1 and 2 closure | M1 J13-J16 | J15-J16 | 2 Minutes | N/A
Friday 19, Saturday 20, Sunday 21 and Monday 22 November | 10pm Friday 19 - 6am Monday 22 | Carriageway closure | M1 J13-J16 | J14-J15 | 30 Minutes | Off at J14 - A509 West to A5 North to A508 East re-join at J15
Junction 14 Entry
Newport Pagnell Services
Southbound
Monday 15 November | 9pm - 5am | Lanes 1 closure | M1 J13-J16 | J15-14 | 2 Minutes | N/A
Monday 15 November | 9pm - 5am | Exit slip closure | M1 J13-J16 | J14 | 15 Minutes | south to J13 exit and return to J14 north exit
Monday 15 November for 4 nights | 9pm - 5am | Lanes 1 and 2 closure | M1 J13-J16 | J15-14 | 2 Minutes | N/A
Monday 15 November for 4 nights | 9pm - 5am | Newport Pagnell Services closure | M1 J13-J16 | Newport Pagnell Services | 2 Minutes | N/A
Monday 15 November for 2 nights | 9pm - 5am | Lanes 1 and 2 closure | M1 J13-J16 | J15a-15 | 2 Minutes | N/A
Monday 15 November for 2 nights | 9pm - 5am | Exit slip closure | M1 J13-J16 | J15 | 2 Minutes | N/A
Monday 15 November for 4 nights | 9pm - 5am | Lanes 3 and 2 closure | M1 J13-J16 | J16-15a | 2 Minutes | N/A
Saturday 13 and Sunday 14 November | No closures