## Sheet1
M1 Northbound
Date | Duration | Details
Monday 4 July | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed Marker Post 82/6 to 89/6
Monday 4 July for 2 nights | 10pm - 6am | Junction 12 - 14 Lanes 1 and 2 closed Marker Post 72/8 to 74/5
Junction 14 - 15a Lanes 1 and 2 closed Marker Post 98/6 to 105/6
Monday 4 July for 4 nights | 9pm - 6am | Junction 15a entry slip closed
Monday 4 July | 9pm - 6am | Junction 15a exit slip closed
Tuesday 5 July | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 85/1 to 90/0
Wednesday 6 July | 10pm - 6am | Junction 13- 14, Lanes 4, 3 and 2 closed Marker Post 78/9 to 80/0
Junction 14 - Junction 15 full carriageway closure
Newport Pagnell Services closed
Junction 14 entry slip closed
| 9pm - 6am | Junction 15 - 15a Lanes 1 and 2 closed Marker Post 101/2 to 106/6
Junction 15a exit slip closed
Thursday 7 July | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 93/4 to 96/1
Junction 14 - 15 Lanes 3 and 2 closed Marker Post 98/4 to 99/4
Junction 15 - Junction 16 full carriageway closure
Junction 15 entry slip closed
Junction 15a entry slip closed
Friday 8 July | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 93/4 to 99/3
Junction 14 - 15a Lanes 1 and 2 closed Marker Post 102/8 to 108/8
Friday 8 July | 8pm - 6am | A45 Northbound full weekend closure from junction 15 roundabout to Wootton - Winvic works
* No planned closures Saturday 9 July and Sunday 10 July
M1 Southbound
Date | Duration | Details
Monday 4 July for 2 nights | 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Friday 8 July | 9pm - 5am | Junction 17 - 16 Lane 3 and 2 closed Marker Post 110/6 to 109/9
Junction 16 - Junction 15 full carriageway closure
Junction 16 entry slip closed
Junction 15a entry slip closed
* No planned closures Saturday 9 July and Sunday 10 July