## Sheet1
M1 Northbound
Date | Duration | Details
Wednesday 24 August for 2 nights | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed Marker Post 82/6 to 83/6
Junction 12 - 14 Lanes 1 and 2 closed Marker Post 71/4 to 77/6
| 9pm - 6am | Junction 15 - 15a Lanes 3 and 2 closed Marker Post 103/1 to 103/9
Junction 15a - Junction 16 full carriageway closure
Junction 15a entry slip closed
Wednesday 24 August for 2 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
Wednesday 24 August for 2 nights | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
* No planned closures Friday 26 August to Monday 29 August
Tuesday 30 August for 2 nights | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed Marker Post 82/6 to 89/6
Tuesday 30 August |  | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 98/6 to 104/4
Tuesday 30 August for 3 nights | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Tuesday 30 August for 4 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
Wednesday 31 August | 10pm - 6am | Junction 12 - 13 Lanes 1 closed Marker Post 68/9 to 69/5
Thursday 1 September for 2 nights | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 88/4 to 94/1
Thursday 1 September | 9pm - 6am | Junction 15 - 17 Lanes 1 and 2 closed Marker Post 103/1 to 110/0
A43 lane 2 closed at junction 15a
Friday 2 September for 3 nights | 9pm - 6am | Junction 15 - 15a Lanes 3 and 2 closed Marker Post 103/1 to 103/9
Junction 15a - Junction 16 full carriageway closure
Junction 15a entry slip closed
Monday 5 September for 3 nights | 9pm - 6am | Junction 14 - 15 Lanes 3 and 2 closed Marker Post 94/2 to 94/9
Junction 14 - 15 Lanes 1, 2 and 3 closed with Hard shoulder running at Marker Post 94/9 to 98/3
Monday 5 September for 5 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
Monday 5 September for 3 nights | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Wednesday 7 September | 10pm - 6am | Junction 13 - 14 Lanes 1 and 2 closed Marker Post 71/1 to 77/5
Thursday 8 September | 10pm - 6am | Junction 12 - 13 Lanes 3 and 2 closed Marker Post 70/6 to 72/6
Junction 13 - Junction 15 full carriageway closure
Junction 13 entry slip closed
Junction 14 entry slip closed
Junction 14 exit slip closed
Newport Pagnell Services closed
Junction 15 exit slip closed
| 9pm - 6am | Junction 15a - 16 Lanes 3 and 2 closed Marker Post 106/0 to 107/5
Friday 9 September | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed Marker Post 78/9 to 85/0
Friday 9 September for 3 nights | 9pm - 6am | Junction 14 - 15 Lanes 3 and 2 closed Marker Post 95/5 to 99/4
Junction 15 - Junction 16 full carriageway closure
Junction 15 entry slip closed
Junction 15a exit slip closed
Junction 15a entry slip closed
Junction 16 exit slip closed
M1 Southbound
Date | Duration | Details
Wednesday 24 August for 2 nights | 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Wednesday 24 August for 2 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
* No planned closures Friday 26 August to Monday 29 August
Tuesday 30 August | 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 13 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Tuesday 30 August for 4 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
Wednesday 31 August for 2 nights | 9pm - 5am | Junction 16 - 15a Lane 3 and 2 closed Marker Post 105/3 to 104/5
Junction 15a - Junction 14 full carriageway closure
Junction 15a entry slip closed
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Thursday 1 September | 9pm - 6am | A43 lane 1 closed at junction 15a
Friday 2 September | 9pm - 6am | Junction 17 - 15 Lane 1 and 2 closed Marker Post 110/6 to 104/0
| 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Friday 2 September | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
* No planned closures Saturday 3 September and Sunday 4 September
Monday 5 September for 3 nights | 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Junction 14 exit slip closed
Monday 5 September for 2 nights | 9pm - 5am | Junction 14 - 13 Lane 1 and 2 closed Marker Post 79/7 to 76/3
Monday 5 September for 5 nights | 8pm - 6am | A45 lane closure for Northampton Gateway construction project
Thursday 8 September | 9pm - 5am | Junction 17 - 15 Lane 3 and 2 closed Marker Post 110/6 to 104/0
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
Junction 15a exit slip closed
Thursday 8 September for 2 nights | 9pm - 5am | Junction 15 - 14 Lane 1 and 2 closed Marker Post 97/3 to 93/7
Thursday 8 September for 2 nights | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Friday 9 September for 3 nights | 9pm - 6am | Junction 16 - 15a Lane 3 and 2 closed Marker Post 107/9 to 106/1