## Sheet1
M1 Northbound
Date | Duration | Details
Tuesday 13 September for 3 nights | 10pm - 6am | Junction 13 - 14 Lanes 4, 3 and 2 closed Marker Post 78/9 to 80/0
Junction 14 - Junction 15 full carriageway closure
Junction 14 entry slip closed
Newport Pagnell Services closed
Tuesday 13 September | 9pm - 6am | Junction 15a - 16 Lanes 3 and 2 closed Marker Post 103/0 to 106/7
Wednesday 14 September | 9pm - 6am | Junction 15a - 16 Lanes 3 and 2 closed Marker Post 102/5 to 105/1
Wednesday 14 September for 2 nights | 8pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
* No planned closures from 6am Friday 16 September to 6am on Tuesday 20 September
Tuesday 20 September | 10pm - 6am | Junction 13 - 14 Lanes 4, 3 and 2 closed Marker Post 78/9 to 80/0
Junction 14 - Junction 15 full carriageway closure
Junction 14 entry slip closed
Newport Pagnell Services closed
Wednesday 21 September | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 93/1 to 97/3
Wednesday 21 September for 2 nights | 9pm - 6am | Junction 15 - 15a Lane 3 and 2 closed Marker Post 101/0 to 102/0
Junction 15 - 15a Lane 3, 2 and 1 closed with Hard shoulder running at Marker Post 102/0 to Junction 15a exit slip
Junction 15a full carriageway closure between the exit slip and entry slip
Thursday 22 September | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 92/1 to 97/3
Friday 23 September | 10pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 93/1 to 97/3
Friday 23 September | 9pm - 6am | Junction 15 - 15a Lane 3 and 2 closed Marker Post 99/8 to 102/0
Junction 15 - 15a Lane 3, 2 and 1 closed with Hard shoulder running at Marker Post 102/0 to Junction 15a exit slip
Junction 15a full carriageway closure between the exit slip and entry slip
Saturday 24 September | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 93/2 to 96/2
Junction 14 - 15a Lane 3 and 2 closed Marker Post 98/2 to 101/3
Junction 15 - 15a Lane 3, 2 and 1 closed with Hard shoulder running at Marker Post 101/3 to 103/2
* No planned closures Sunday 25 September
Monday 26 September for 2 nights | 9pm - 6am | Junction 15 - 15a Lane 3 and 2 closed at Marker Post 101/7 to 102/9
Junction 15 - 15a Lane 3, 2 and 1 closed with Hard shoulder running at Marker Post 102/9 to 103/9
Junction 15a full carriageway closure between the exit slip and entry slip
Junction 15a - 17 Lane 1 and 2 closed at Marker Post 106/9 to 110/4
Monday 26 September for 2 nights | 9pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 94/9 to 99/1
Tuesday 27 September for 3 nights | 10pm - 6am | Junction 15 - 15a Lane 4 and 3 closed at Marker Post 83/3 to 88/1
Wednesday 28 September for 3 nights | 9pm - 6am | Junction 15 - 15a Lane 3 and 2 closed at Marker Post 103/1 to 103/9
Junction 15a full carriageway closure between the exit slip and entry slip
Wednesday 28 September | 9pm - 6am | Junction 15a - 16 Lane 3, 2 and 1 closed with Hard shoulder running from junction 15a entry slip to Marker Post 104/8
Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 96/5 to 98/4
Junction 15a - 17 Lane 1 and 2 closed at Marker Post 107/3 to 110/4
Thursday 29 September | 9pm - 6am | Junction 15a - 16 Lane 3, 2 and 1 closed with Hard shoulder running from junction 15a entry slip to Marker Post 105/2
Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 94/9 to 99/1
Junction 15a - 17 Lane 1 and 2 closed at Marker Post 107/7 to 110/4
Friday 30 September | 9pm -6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 96/9 to 99/1
* No planned closures Saturday 1 October and Sunday 2 October
M1 Southbound
Date | Duration | Details
Wednesday 14 September | 9pm - 6am | Junction 17 - 16 Lane 3 and 2 closed Marker Post 110/6 to 109/9
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
Junction 15a exit slip closed
Wednesday 14 September | 8pm - 6am | A45 carriageway closure for Northampton Gateway construction project
Wednesday 14 September | 9pm - 6am | Junction 15a - 14 Lane 1 and 2 closed Marker Post 101/1 to 97/9
Thursday 15 September | 9pm - 6am | Junction 16 - 15a Lane 1 and 2 closed Marker Post 105/5 to 104/3
Junction 15 - 14 Lane 1 and 2 closed Marker Post 99/8 to 95/9
| 9pm - 5am | Junction 15 - 14 Lane 3 and 2 closed Marker Post 89/0 to 86/3
* No planned closures from 6am Friday 16 September to 6am on Tuesday 20 September
Tuesday 20 September | 9pm - 6am | Junction 19 - 18 Lane 4,3 and 2 closed Marker Post 128/0 to 127/0
Junction 18 - Junction 16 full carriageway closure
Junction 18 entry slip closed
M45 Lane 2 closed Marker Post 11/4 to 10/8
M45 full carriageway closure J1 to 0
Junction 16 exit slip closed
Junction 16 - 15 Lane 1 and 2 closed Marker Post 105/2 to 97/6
Junction 14 - 13 Lane 1 and 2 closed Marker Post 75/5 to 74/2
Wednesday 22 September for 2 nights | 9pm - 5am | Junction 15a - 15 Lane 3 and 2 closed Marker Post 101/2 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services exit slip closed
Junction 14 exit slip closed
Friday 23 September | 9pm - 5am | Junction 15 - 14 Lane 1 and 2 closed Marker Post 91/0 to 84/8
Saturday 24 September | 9pm - 5am | Junction 19 - 18 Lane 4,3 and 2 closed Marker Post 128/0 to 127/0
Junction 18 - Junction 16 full carriageway closure
Junction 18 entry slip closed
M45 Lane 2 closed Marker Post 11/4 to 10/8
M45 full carriageway closure J1 to 0
Junction 16 exit slip closed
* No planned closures Sunday 25 September
Monday 26 September for 2 nights | 9pm - 5am | Junction 15 - 14 Lane 1 and 2 closed Marker Post 101/2 to 95/8
Tuesday 27 September for 3 nights | 9pm - 5am | Junction 15 - 14 Lane 4 and 3 closed Marker Post 88/6 to 83/9
Wednesday 28 September for 2 nights | 9pm - 5am | Junction 15 - 14 Lane 1 and 2 closed Marker Post 98/0 to 93/9
Friday 30 September | 9pm - 5am | Junction 16 - 15 Lane 1 and 2 closed Marker Post 105/2 to 100/0
* No planned closures Saturday 1 October and Sunday 2 October