## Sheet1
M1 Northbound
Date | Duration | Details
Monday 21 November | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 85/7 to 92/8
Monday 21 November for 2 nights | 9pm - 6am | Junction 14 - 15a Lanes 1, 2 and 3 closed at Marker Post 96/8 to 100/1
Junction 15 exit slip closed
Tuesday 22 November | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 87/8 to 94/3
Wednesday 23 November | 10pm - 6am | Junction 14 - 15a Lanes 1, 2 and 3 closed at Marker Post 92/5 to 96/8
Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 83/4 to 87/9
Thursday 24 November | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 85/6 to 89/4
| 9pm - 6am | Junction 15 - 16 Lanes 1 and 2 closed Marker Post 100/8 to 104/3
Thursday 24 November for 2 nights | 9pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 92/8 to 98/3
Friday 25 November |  | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 83/4 to 89/4
* No planned closures Saturday 26 November and Sunday 27 November
Monday 28 November | 10pm - 6am | Junction 13 - 15 Lanes 1 and 2 closed at Marker Post 78/6 to 80/6
Tuesday 29 November | 10pm - 6am | Junction 13 - 15 Lanes 1 and 2 closed at Marker Post 79/1 to 81/2
Wednesday 30 November | 10pm - 6am | Junction 13 - 15 Lanes 1 and 2 closed at Marker Post 79/1 to 81/8
Thursday 1 December | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 82/9 to 87/0
Friday 2 December for 3 nights | 10pm - 6am | Junction 13 - 15 Lanes 2, 3 and 4 closed at Marker Post 78/9 to 80/0
Junction 14 - Junction 15 full carriageway closure
Junction 14 entry slip closed
Newport Pagnell Services closed
Monday 5 December for 2 nights | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 83/4 to 90/4
Monday 5 December for 3 nights | 9pm - 6am | Junction 14 - 15 Lanes 4, 3 and 2 closed at Marker Post 98/5 to 99/4
Junction 15 - Junction 16 full carriageway closure
Junction 15 entry slip closed
Junction 15a entry slip closed
Wednesday 7 December | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 85/8 to 93/1
Thursday 8 December | 10pm - 6am | Junction 13 - 14 Lanes 1 and 2 closed at Marker Post 78/9 to 80/2
Junction 13 exit slip Lane 1 closed
Thursday 8 December | 9pm - 6am | Junction 15 - 15a Lanes 2, 3 and 4 closed Marker Post 103/0 to 103/9
Junction 15a - Junction 16 full carriageway closure
Junction 15a entry slip closed
Friday 9 December | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 92/9 to 99/5
Junction 15 - 15a Lanes 2, 3 and 4 closed Marker Post 103/0 to 103/9
Junction 15a - Junction 18 full carriageway closure
Junction 15a entry slip closed
Friday 9 December for 2 nights | 9pm - 6am | Junction 16 entry slip closed
Saturday 10 December | 9pm - 6am | Junction 15a - 16 Lanes 1 and 2 closed Marker Post 109/4 to 110/5
* No planned closures Sunday 11 December
M1 Southbound
Date | Duration | Details
Monday 21 November | 9pm - 5am | Junction 16 - 15 Lanes 1, 2 and 3 closed at Marker Post 105/5 to 99/6
Junction 15 exit slip mobile Lane 1
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 89/9 to 86/3
Tuesday 22 November | 9pm - 5am | Junction 17 - 15a Lane 1, 2 and 3 closed Marker Post 110/8 to 104/3
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 90/2 to 83/2
Tuesday 22 November for 2 nights | 9pm - 5am | Junction 15a exit slip closed
Wednesday 23 November | 9pm - 5am | Junction 16 - 15 Lanes 1, 2 and 3 closed at Marker Post 106/5 to 102/2
Junction 15a entry slip closed
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 96/7 to 89/7
Thursday 24 November | 9pm - 5am | Junction 16 - 15 Lanes 1, 2 and 3 closed at Marker Post 105/5 to 101/1
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 92/9 to 86/4
Friday 25 November | 9pm - 5am | Junction 15a - 15 Lane 2 and 3 closed at Marker Post 101/4 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services closed
* No planned closures Saturday 26 November and Sunday 27 November
Monday 28 November | 9pm - 5am | Junction 15 - 13 Lanes 1 and 2 closed at Marker Post 81/7 to 77/0
Tuesday 29 November | 9pm - 5am | Junction 15 - 13 Lanes 1 and 2 closed at Marker Post 81/7 to 80/7
Wednesday 30 November | 9pm - 5am | Junction 15 - 13 Lanes 1 and 2 closed at Marker Post 83/3 to 80/7
Thursday 1 December | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 83/3 to 81/7
Friday 2 December | 9pm - 5am | Junction 15a - 14 Lanes 1, 2 and 3 closed at Marker Post 101/3 to 95/1
* No planned closures Saturday 3 December and Sunday 4 December
Monday 5 December | 9pm - 5am | Junction 16 - 15 Lanes 2, 3 and 4 closed at Marker Post 105/6 to 103/0
Monday 5 December for 3 nights | 9pm - 5am | Junction 15 - 14 Lanes 2, 3 and 4 closed at Marker Post 98/1 to 93/6
Tuesday 6 December for 2 nights | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 90/6 to 86/2
Thursday 8 December | 9pm - 5am | Junction 15a - 15 Lane 2, 3 and 4 closed at Marker Post 101/3 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services closed
Friday 9 December | 9pm - 5am | Junction 16 - 15 Lanes 2, 3 and 4 closed at Marker Post 105/6 to 102/2
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 93/0 to 86/2
Saturday 10 December for 2 nights | 9pm - 6am | Junction 15a - 15 Lane 2, 3 and 4 closed at Marker Post 101/3 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services closed