## Sheet1
M1 Northbound
Date | Duration | Details
Monday 2 January (12am) to Sunday 8 January (11:59pm) | 24hrs a day | Junction 15 entry slip hard shoulder closure for Northampton Gateway construction project
Tuesday 3 January (9pm) to Saturday 4 February (6am) | 24hrs a day | Junction 16 exit slip closed
Tuesday 3 January | 9pm - 6am | Junction 15a - 16 Lanes 3 and 4 closed at Marker Post 106/2 to 107/1
Wednesday 4 January | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 95/5 to 99/5
Junction 15 - 15a Lanes 2, 3 and 4 closed at Marker Post 103/0 to 103/9
Junction 15a - Junction 18 full carriageway closure
Junction 15a entry slip closed
Junction 16 entry slip closed
Tuesday 4 January (12am) to Sunday 8 January (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
Tuesday 4 January for 3 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Tuesday 4 January for 3 nights | 8pm - 6am | Junction 15 roundabout Lane closure for Northampton Gateway construction project
Thursday 5 January for 2 nights | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 88/4 to 94/5
| 9pm - 6am | Junction 14 - 15 Lanes 2, 3 and 4 closed at Marker Post 98/5 to 99/4
Junction 15 - Junction 16 full carriageway closure
Junction 15 entry slip closed
Junction 15a entry slip closed
* No planned closures on Saturday 7 January and Sunday 8 January 2023
Monday 9 January | 10pm - 6am | Junction 13 - 15 Lanes 1 and 2 closed at Marker Post 78/4 to 80/1
Monday 9 January for 2 nights | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 94/9 to 99/7
Monday 9 January for 2 nights | 9pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Wednesday 11 January for 3 nights | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 83/4 to 89/7
Friday 13 January | 9pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 94/3 to 98/2
* No planned closures on Saturday 14 January and Sunday 15 January 2023
Monday 16 January for 2 nights | 9pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 95/9 to 100/6
Junction 15 - 16 Lanes 1 and 2 closed at Marker Post 103/1 to 109/8
Junction 15 exit slip closed
Monday 16 January for 2 nights | 9pm - 6am | Junction 15 entry slip closed for Northampton Gateway construction project
Wednesday 18 January | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 82/7 to 89/6
Wednesday 18 January | 9pm - 6am | Junction 15 - 15a Lanes 2, 3 and 4 closed at Marker Post 103/0 to 103/9
Junction 15a - Junction 16 full carriageway closure
Junction 15a entry slip closed
Thursday 19 January | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 82/7 to 84/7
Junction 15 - 15a Lanes 1, 2, and 3 closed at Marker Post 101/2 to 103/0
Friday 20 January | 9pm - 6am | Junction 15 - 15a Lanes 1, 2, and 3 closed at Marker Post 101/2 to 108/2
* No planned closures on Saturday 21 January and Sunday 22 January 2023
M1 Southbound
Date | Duration | Details
Tuesday 3 January | 9pm - 6am | Junction 16 - 15a Lanes 3 and 4 closed at Marker Post 107/7 to 106/8
Wednesday 4 January for 2 nights | 9pm - 6am | Junction 16 - 15 Lanes 1 and 2 closed at Marker Post 105/5 to 100/1
Tuesday 4 January (12am) to Sunday 8 January (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
Tuesday 4 January for 3 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Friday 6 January | 9pm - 6am | Junction 16 - 15 Lanes 1 and 2 closed at Marker Post 107/8 to 101/7
* No planned closures on Saturday 7 January and Sunday 8 January 2023
Monday 9 January | 9pm - 6am | Junction 16 - 15 Lanes 1 and 2 closed at Marker Post 105/5 to 102/4
Junction 15a exit slip closed including A43 access into services
| 9pm - 5am | Junction 14 - 13 Lanes 1 and 2 closed at Marker Post 77/1 to 74/4
Tuesday 10 January for 2 nights | 9pm - 6am | Junction 16 - 15 Lanes 1, 2 and 3 closed at Marker Post 105/5 to 101/1
Junction 15a entry slip closed
Tuesday 10 January | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 94/3 to 92/7
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 89/8 to 83/1
Wednesday 11 January | 9pm - 6am | Junction 15a exit slip closed including A43 access into services
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 97/7 to 91/4
Thursday 12 January | 9pm - 6am | Junction 15a - 14 Lanes 1, 2 and 3 closed at Marker Post 101/3 to 94/3
Junction 15 entry slip closed
Friday 13 January | 9pm - 6am | Junction 15a - 14 Lanes 1, 2 and 3 closed at Marker Post 100/0 to 95/3
| 9pm - 5am | Junction 14 - 13 Lanes 1 and 2 closed at Marker Post 76/8 to 73/4
* No planned closures on Saturday 14 January and Sunday 15 January 2023
Monday 16 January | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
Monday 16 January for 2 nights | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 83/6 to 81/8
Tuesday 17 January | 9pm - 6am | Junction 17 - 15a Lanes 1, 2 and 3 closed Marker Post 110/8 to 107/5
Wednesday 18 January | 9pm - 6am | Junction 17 - 15a Lanes 1, 2 and 3 closed Marker Post 110/8 to 105/1
Junction 15a - 14 Lanes 1, 2 and 3 closed at Marker Post 101/3 to 98/9
Wednesday 18 January | 9pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Junction 15 entry slip closed for Northampton Gateway construction project
Thursday 19 January | 9pm - 6am | Junction 16 - 15a Lanes 1, 2 and 3 closed Marker Post 106/8 to 105/1
Junction 15 - 14 Lanes 1, 2 and 3 closed at Marker Post 97/7 to 94/9
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 90/7 to 86/2
Friday 20 January | 9pm - 6am | Junction 16 - 15a Lane 2, 3 and 4 closed at Marker Post 106/0 to 104/5
Junction 15a - Junction 15 full carriageway closure
Junction 15a entry slip closed
Junction 15 - 14 Lanes 1, 2 and 3 closed at Marker Post 96/5 to 93/4
Friday 20 January | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 83/6 to 81/8
* No planned closures on Saturday 21 January and Sunday 22 January 2023