## Sheet1
M1 Northbound
Date | Duration | Details
Tuesday 31 January (9pm) to Saturday 4 February (6am) | 24hrs a day | Lane 1 Junction 16 exit slip closed
Monday 23 January | 9pm - 6am | Junction 15 - 16 Lanes 1, 2 and 3 closed at Marker Post 102/1 to 106/0
Monday 23 January for 2 nights | 9pm - 6am | Junction 15a exit slip closed
Monday 23 January (12am) to Sunday 29 January (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
| 24hrs a day | Junction 15 entry slip hard shoulder closure for Northampton Gateway construction project
Monday 23 January for 6 nights | 8pm - 6am | Junction 15 roundabout Lane closure for Northampton Gateway construction project
A45 Lane closure for Northampton Gateway construction project
Tuesday 24 January | 10pm - 6am | Junction 13 - 14 Lanes 2, 3, and 4 closed at Marker Post 78/9 to 80.0
Junction 14 - Junction 15 full carriageway closure
Junction 14 entry slip closed
Newport Pagnell Services closed
Tuesday 24 January | 9pm - 6am | Junction 15 - 16 Lanes 1, 2 and 3 closed at Marker Post 102/4 to 106/0
Junction 15a entry slip closed
Wednesday 25 January | 9pm - 6am | Junction 15a - 17 Lanes 1, 2 and 3 closed at Marker Post 104/9 to 110/4
Junction 16 entry slip closed
Thursday 26 January for 2 nights | 9pm - 6am | Junction 15a - 17 Lanes 1, 2 and 3 closed at Marker Post 107/3 to 109/2
Junction 16 exit slip closed
* No planned closures on Saturday 28 January and Sunday 29 January 2023
Monday 30 January | 10pm - 6am | Junction 13 - 14 Lanes 1, 2 and 3 closed at Marker Post 75/8 to 76/8
| 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 95/4 to 99/8
Monday 30 January | 9pm - 6am | Junction 15 exit slip closed for Northampton Gateway construction project
Tuesday 31 January (6am) to Sunday 12 February (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
Monday 30 January | 12am - 9pm | Junction 15 entry slip hard shoulder closure for Northampton Gateway construction project
Monday 30 January | 9pm - 6am | Junction 15 entry slip closed for Northampton Gateway construction project
Monday 30 January for 5 nights | 8pm - 6am | Junction 15 roundabout Lane closure for Northampton Gateway construction project
A45 Lane closure for Northampton Gateway construction project
Tuesday 31 January (6am) to Sunday 12 February (11:59pm) | 24hrs a day | Junction 15 entry slip hard shoulder closure for Northampton Gateway construction project
Tuesday 31 January | 10pm - 6am | Junction 13 - 15 Lanes 1 and 2 closed at Marker Post 79/2 to 86/5
| 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 95/4 to 96/6
Junction 15 - 16 Lanes 1 and 2 closed at Marker Post 102/8 to 104/9
Junction 15a exit slip closed
Junction 15a exit slip closed
Wednesday 1 February | 9pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 95/4 to 97/8
Junction 15 - 16 Lanes 1 and 2 closed at Marker Post 103/1 to 106/4
Thursday 2 February | 10pm - 6am | Junction 14 - 15 Lanes 1 and 2 closed at Marker Post 88/9 to 92/6
| 9pm - 6am | Junction 14 - 16 Lanes 1 and 2 closed at Marker Post 99/7 to 105/6
Thursday 2 February | 9pm - 6am | Junction 15 entry slip closed for Northampton Gateway construction project
Friday 3 February | 9pm - 6am | Junction 14 - 15 Lanes 1, 2 and 3 closed at Marker Post 95/5 to 98/5
Junction 15 - 16 Lanes 1 and 2 closed at Marker Post 103/1 to 106/4
Saturday 4 February | 9pm - 6am | Junction 15a - 17 Lanes 1, 2 and 3 closed at Marker Post 108/1 to 110/5
Junction 16 entry slip closed
* No planned closures on Sunday 5 February 2023
Monday 6 February | 9pm - 6am | Junction 14 - 15a Lanes 1, 2 and 3 closed at Marker Post 94/9 to 100/6
Junction 15 entry slip closed
Tuesday 7 February for 5 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Junction 15 roundabout Lane closure for Northampton Gateway construction project
Tuesday 7 February | 9pm - 6am | Junction 14 - 15a Lanes 1, 2 and 3 closed at Marker Post 94/9 to 99/6
Tuesday 7 February for 2 nights | 9pm - 6am | Junction 15 exit slip closed
Wednesday 8 February | 9pm - 6am | Junction 14 - 15a Lanes 1, 2 and 3 closed at Marker Post 97/3 to 99/4
Friday 10 February | 9pm - 6am | Junction 15 - 16 Lanes 1, 2 and 3 closed at Marker Post 101/5 to 105/9
Junction 15a entry slip closed
Saturday 11 February | 9pm - 6am | Junction 14 - 15 Lanes 4, 3 and 2 closed at Marker Post 98/3 to 99/4
Junction 15 - Junction 16 full carriageway closure
Junction 15 entry slip closed
Junction 15a entry slip closed
* No planned closures on Sunday 12 February 2023
M1 Southbound
Date | Duration | Details
Monday 23 January | 9pm - 6am | Junction 17 - 16 Lanes 1, 2 and 3 closed Marker Post 112/7 to 111/4
Monday 23 January (6am) to Sunday 29 January (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
Monday 23 January for 6 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Wednesday 25 January | 9pm - 5am | Junction 15a - 15 Lanes 2, 3 and 4 closed at Marker Post 101/3 to 100/2
Junction 15 - Junction 14 full carriageway closure
Junction 15 entry slip closed
Newport Pagnell Services closed
Thursday 26 January | 9pm - 5am | Junction 15 - 14 Lanes 1, 2 and 3 closed at Marker Post 88/8 to 87/4
Junction 14 exit slip closed
Junction 15 - 13 Lanes 1, 2 and 3 closed at Marker Post 82/3 to 80/8
Friday 27 January | 9pm - 6am | Junction 16 - 15 Lanes 2, 3 and 4 closed at Marker Post 105/5 to 101/6
* No planned closures on Saturday 28 January and Sunday 29 January 2023
Monday 30 January | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
Monday 30 January for 2 nights | 9pm - 6am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 98/5 to 97/3
Monday 30 January | 9pm - 5am | Junction 15 - 13 Lanes 1 and 2 closed at Marker Post 82/5 to 74/7
Monday 30 January (6am) to Sunday 12 February (11:59pm) | 24hrs a day | Junction 15 exit slip Lane 1 closure for Northampton Gateway construction project
Monday 30 January for 6 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Tuesday 31 January | 9pm - 5am | Junction 16 - 15a Lanes 1, 2, and 3 closed at Marker Post 106/6 to 104/6
Wednesday 1 February | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15 full carriageway closure
Junction 16 entry slip closed
Wednesday 1 February | 9pm - 5am | Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 95/1 to 88/1
Wednesday 1 February for 2 nights | 9pm - 6am | Junction 15a entry slip closed
Thursday 2 February | 9pm - 6am | Junction 16 - 15 Lanes 1, 2 and 3 closed at Marker Post 105/5 to 101/6
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 98/5 to 95/3
Friday 3 February | 9pm - 6am | Junction 16 - 15 Lanes 1 and 2 closed at Marker Post 105/5 to 100/2
Junction 15 - 14 Lanes 1 and 2 closed at Marker Post 96/3 to 95/3
Friday 3 February | 9pm - 6am | Junction 15 entry slip closed for Northampton Gateway construction project
Junction 15 exit slip closed for Northampton Gateway construction project
* No planned closures on Saturday 4 February and Sunday 5 February 2023
Monday 6 February | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15 full carriageway closure
Junction 16 entry slip closed
Junction 15a entry slip closed
Monday 6 February for 3 nights | 9pm - 6am | Junction 15a - 15 Lanes 1 and 2 closed at Marker Post 101/9 to 101/0
Tuesday 7 February for 5 nights | 8pm - 6am | A45 Lane closure for Northampton Gateway construction project
Tuesday 7 February |  | Junction 15 entry slip closed for Northampton Gateway construction project
Tuesday 7 February for 2 nights | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
Thursday 9 February | 9pm - 6am | Junction 19 - 18 Lanes 2, 3 and 4 closed at Marker Post 128/0 to 127/0
Junction 18 - Junction 15a full carriageway closure
Junction 18 entry slip closed
M45 Lane 2 closed Marker Post 11/4 to 10/8
M45 full carriageway closure J1 to 0
Junction 16 entry slip closed
Junction 15 exit slip closed
Thursday 9 February for 2 nights | 9pm - 6am | Junction 15a - 14 Lanes 1 and 2 closed at Marker Post 101/9 to 99/4
Friday 10 February | 9pm - 6am | Junction 17 - 16 Lanes 2, 3 and 4 closed Marker Post 110/8 to 109/9
Junction 16 - Junction 15a full carriageway closure
Junction 16 entry slip closed
* No planned closures on Saturday 11 February and Sunday 12 February 2023